## 1. M&E Framework
Increasing the integrity in public procurement
Overall Goal: Increased public procurement transparency through citizen/CSO monitoring and reporting in Moldova to hold stakeholders involved in public procurement processes accountable, inducing them to operate with integrity to perform their duties more effectively.
Objective 1 - Capacity Building: Moldovan CSOs and journalists are sufficiently equipped to conduct meaningful monitoring of procurement processes.
Phase | Activity | KPI | Description | Result Level | Data Source | Baseline | Target | Actual | Status
1. Inpception | a. Inception Report | 1. Number of interviews held | Ensure quality of the baseline study | Output | Inception Report | 0 interviews held | ≥ 10 interviews conducted | 23 interviews with 27 stakeholders | Complete
|  | 2. Number of CSOs and journalists completing the online survey | Determine the level of knowledge and experience of CSOs and journalists in PP monitoring | Output | Inception Report | 0 surveys conducted | ≥ 1 online survey conducted | 1 online survey conducted | Complete
2. Training | a. Training of monitors & journalists | 3. Number of training sessions held | Build capacity: deliver training on procurement monitoring | Output | Training Report | 0 training sessions held | ≥ 12 training sessions over 3 months held | 24 training sessions in 12 modules delivered | Complete
|  | 4. Civil Society Organisations trained and supported | Build capacity: CSOs are trained on monitoring procurement | Output | Training Report | 0 CSOs trained | ≥ 20 CSOs organizations trained | 29 CSOs trained and supported | Complete
|  | 5. Number of journalists trained and supported | Build capacity: journalists are trained on monitoring procurement | Output | Training Report | 0 journalists trained | ≥5 journalists trained | 11 journalists trained and supported | Complete
Objective 2 - Active Monitoring: Procurement procedures and practices are appropriately monitored by Moldovan CSOs and journalists making use of the e-procurement system and other sources of information.
Phase | Activity | Indicator | Description | Result Level | Data Source | Baseline | Target | Actual | Status
3: Monitoring | a. Grants Program | 6. Number of grant facility guidelines | Prepare robust and transparent documentation to guide the grants process | Output | Guideline document | 0 grant facility guidelines | ≥1 grant facility guideline | 2 guidelines documents elaborated by and published | Complete
|  | 7. Number of CSOs receiving assistance engaged in advocacy interventions | Provide financial and technical support to a suitable grantees to conduct effective monitoring activities | Output | Monitoring Reports 1 & 2 | 0 grantees supported | ≥ 10 grantees/ projects for a total of US$300k | 13 grants provided to 11 different grantees in two rounds for a total value of US$301,835 | Complete
|  | 8. Number of mentoring sessions provided to each grantee | Ensure quality of the monitoring activities by grantees through tehcnical guidance and mentoring | Output | Monitoring Reports | 0 mentoring sessions | ≥1 mentoring session per grantee per quarter ≥40 mentoring sessions for all grantees until the end of the project | 76 mentoring sessions provided as follows: Round 1: 48 sessions for 8 grantees; Round 2: 28 sessions for 5 grantees In both rounds, each grantee received a minimum of 1 session per quarter | Complete
|  | 9. Number of grantees that improve their effectiveness in procurement monitoring | Strentghen the capacity of CSOs engaged in monitoring public procurement through the grants program | Outcome | Evaluation Reports | 0 grantees with improved capacity in proucrement monitoring | ≥5 grantees improve their effectiveness in procurement monitoring | 23 grantees self-assessed a (very) strong improvement in their effectiveness of procurement monitoring as follows: Round 1 : 12 individuals Round 2: 11 individuals | Complete
|  | 10. Number of monitoring reports provided by grantees | Document and measure the results (outputs, outcomes, impact) produced by the grants process by developing and collecting strong data. | Outcome | Monitoring Reports | 0 reports with action-oriented recommendations | ≥1 report per grantee | 13 reports with findings and recommendations as follows: Round 1: 8 reports (1 per grantee) Round 2: 5 reports (2 per grantee) | Complete
| b. Digital Platform | 11. Number of active users | Develop and operate a digital platform that supports the Moldovan community of procurement monitoring | Outcome | Google Analytics | 0 active users | 30 active users (unique users visiting the platform) | ~80 active users (average since launch), 955 active users (latest monthy report April 2025) | Complete
|  | 12. Number of uploaded materials | Develop and publish resources that support the Moldovan community of procurement monitoring | Output | Digital Platform | 0 materials uploaded | 6 materials uploaded per quarter, 1 per section (ask an expert, NPPP, coalition, news, newsletter, resources) | 408 published posts and materials on the website. More than 6 per quarter and 1 per each section. | Complete
| c. Coalition Building - Coalition of Monitors | 13. Number of CSOs members of the monitoring coalition | Convene and operate a CSO coalition on Monitoring to foster cooperation as well as formulation & submission of recommendations to strengthen public procurement. | Output | Coalition Building Report | 0 monitoring CSOs members of the coalitions | 15 CSOs joining the Coalition of Monitors as members | 31 individuals representing 24 CSO, media outlets and academic institutions enlisted as coallition members (as of April 2025) | Complete
| c. Coalition Building - Multi-Stakeholder Dialogue | 14. Number of members of the National Platform on Public Procurement | Convene and operate a multi-stakeholder dialogue to facilitate formulation and submission of recommendations to strengthen public procurement | Output | Minutes of NPPP meetings | 0 members of the NPPP | 12 NPPP member entities representing all sectors | 19 NPPP members including stakeholders from all sectors (government, civil society, private sector) (as of April 2025) | Complete
| d. Monitoring Results - Findings (case-based) | 15. Number of case-related submissions to relevant authorities | Case-related findings are submitted to relevant recipients (CAs, control-, anti- corruption and other legal bodies), to address a defective procurement or general procurement processes by grantees | Outcome | Results Tracker | 0 case-related findings formulated and submitted to relevant stakeholders | ≥10 grantees’ and monitoring coalition’s case-related submissions | 23 case-related submissions | Complete
Objective 3 - Corrective Action and Advocacy: Findings and recommendations resulting from credible and professional CSO monitoring are taken seriously and acted upon by contracting entities, contractors and government oversight and law enforcement entities including the National Anti-Corruption Center
Phase | Activity | Indicator | Description | Result Level | Data Source | Baseline | Target | Actual | Status
| d. Monitoring Results - Recommen-dations (system-relevant) | 16. Number of system-related recommendations to relevant authorities | System-related recommendations are submitted to relevant recipients (CAs, control-, anti- corruption & other legal bodies) by grantees, coalition, NPPP | Outcome | Results Tracker | 0 system-related recommenda-tions submitted to relevant stakeholders | ≥ 5 monitoring recommendations formulated and submitted by grantees directly or indirectly through NPPP | 175 recommendations formulated and submitted to relevant recipients | Complete
| d. Monitoring Results - Change achieved | 17. Number of recommendations that led to change: laws, policies or procedures adopted, revised, stalled or changed | Action is taken by contracting authorities, control bodies and other government bodies by taking up recommendations to address a defective procurement or general procurement processes | Outcome | Results Tracker | 0 laws, policies or procedures adopted, revised, stalled, or changed | ≥2 laws, policies or procedures adopted, revised, stalled, or changed | 21 recommendations related to laws, policies or procedures adopted, revised, stalled, changed, or committed to do so by relevant recipients | Complete
4. Publicity | a. Visibilty - through PR activities | 18. Number of press releases and newsletters | Project activities are documented in press releases and newsletter disseminated to a wider public | Output | Publicity Report | 0 press releases; 0 newsletters | ≥ 1 press release per quarter ≥ 1 newsletter per quarter | 1. Press releases: 65 (55 issued by IDIS, 10 issued by PTF) 2. Newsletters: 14 editions 3. Grantee materials: 297 documents | Complete
| a. Visibility - contributes to political leverage | 19. Number of references in other media | Other media refer to press releases and newsletters | Outcome | Publicity Report | 0 reference in other media | ≥ 1 reference in other media per quarter | 218 references in Moldovan national and local media and online media, with more than 1 each project quarter | Complete